## Project Overview
SIIV APARTMENTS — MAAMULPRO TEST PROJECT
Project Name | Siiv Apartments
Description | G+5 apartment building planned for rental apartments and selected office/commercial units.
Building Type | G+5, Ground + 5 floors
Planned Use | Rental apartments + selected office/commercial units
Location | Mogadishu, Somalia
Start Date | 2026-01-01
Planned 6-Month Phase End | 2026-06-30
Physical Progress | 70%
Budget | 250000
Actual Spent | 177065
Remaining Budget | 72935
Financial Utilization | 70.83%
Status | Socda, 70% physical progress
Main Cost Areas | Materials, subcontractors, daily labor, monthly payroll, site overhead
Xogtan waa Test Data loogu talagalay MaamulPro, ma aha xog shirkad dhab ah.

## Staff
Shaqaalaha Siiv Apartments
Employee ID | Magaca | Doorka | Nooca | Qiimaha | Unit
EMP-001 | Xuseen Ismaaciil | Maamule Mashruuc | Bille | 700 | $/Month
EMP-002 | Daahir Sheekh | Injineer Goobta | Bille | 550 | $/Month
EMP-003 | Maxamed Cumar | Agaasime Guud / Kormeer | Bille | 900 | $/Month
EMP-004 | Cabdi Nuur Xasan | Xisaabiye Mashruuc | Bille | 500 | $/Month
EMP-005 | Saalax Axmed | Kormeeraha Shaqada | Bille | 450 | $/Month
EMP-006 | Guuleed Cabdi | Fuundi | Maalinle | 18 | $/Day
EMP-007 | Cabdiqaadir Ismaaciil | Birlaha / Steel Fixer | Maalinle | 17 | $/Day
EMP-008 | Faarax Warsame | Kaarpender | Maalinle | 16 | $/Day
EMP-009 | Aweys Barre | Shaqaale Caadi | Maalinle | 12 | $/Day
EMP-010 | Bashiir Yuusuf | Shaqaale Caadi | Maalinle | 12 | $/Day
EMP-011 | Axmed Maxamed | Kaaliye | Maalinle | 10 | $/Day
EMP-012 | Saciid Aadan | Shaqaale Caadi | Maalinle | 12 | $/Day
EMP-013 | Yahye Maxamed | Mashiin / Mixer Operator | Maalinle | 20 | $/Day

## Daily Attendance
Xaadirinta iyo Mushaharka Shaqaalaha Maalinlaha ah
Project | Employee ID | Magaca | Xirfadda | Bisha | Maalmo Shaqeeyay | Qiimaha/Day | Wadarta
PRJ-001 | EMP-006 | Guuleed Cabdi | Fuundi | Janaayo 2026 | 25 | 18 | 450
PRJ-001 | EMP-006 | Guuleed Cabdi | Fuundi | Febraayo 2026 | 20 | 18 | 360
PRJ-001 | EMP-006 | Guuleed Cabdi | Fuundi | Maarso 2026 | 20 | 18 | 360
PRJ-001 | EMP-006 | Guuleed Cabdi | Fuundi | Abriil 2026 | 25 | 18 | 450
PRJ-001 | EMP-006 | Guuleed Cabdi | Fuundi | Maajo 2026 | 22 | 18 | 396
PRJ-001 | EMP-006 | Guuleed Cabdi | Fuundi | Juun 2026 | 21 | 18 | 378
PRJ-001 | EMP-007 | Cabdiqaadir Ismaaciil | Birlaha / Steel Fixer | Janaayo 2026 | 21 | 17 | 357
PRJ-001 | EMP-007 | Cabdiqaadir Ismaaciil | Birlaha / Steel Fixer | Febraayo 2026 | 21 | 17 | 357
PRJ-001 | EMP-007 | Cabdiqaadir Ismaaciil | Birlaha / Steel Fixer | Maarso 2026 | 25 | 17 | 425
PRJ-001 | EMP-007 | Cabdiqaadir Ismaaciil | Birlaha / Steel Fixer | Abriil 2026 | 20 | 17 | 340
PRJ-001 | EMP-007 | Cabdiqaadir Ismaaciil | Birlaha / Steel Fixer | Maajo 2026 | 25 | 17 | 425
PRJ-001 | EMP-007 | Cabdiqaadir Ismaaciil | Birlaha / Steel Fixer | Juun 2026 | 25 | 17 | 425
PRJ-001 | EMP-008 | Faarax Warsame | Kaarpender | Janaayo 2026 | 24 | 16 | 384
PRJ-001 | EMP-008 | Faarax Warsame | Kaarpender | Febraayo 2026 | 20 | 16 | 320
PRJ-001 | EMP-008 | Faarax Warsame | Kaarpender | Maarso 2026 | 24 | 16 | 384
PRJ-001 | EMP-008 | Faarax Warsame | Kaarpender | Abriil 2026 | 23 | 16 | 368
PRJ-001 | EMP-008 | Faarax Warsame | Kaarpender | Maajo 2026 | 20 | 16 | 320
PRJ-001 | EMP-008 | Faarax Warsame | Kaarpender | Juun 2026 | 20 | 16 | 320
PRJ-001 | EMP-009 | Aweys Barre | Shaqaale Caadi | Janaayo 2026 | 20 | 12 | 240
PRJ-001 | EMP-009 | Aweys Barre | Shaqaale Caadi | Febraayo 2026 | 21 | 12 | 252
PRJ-001 | EMP-009 | Aweys Barre | Shaqaale Caadi | Maarso 2026 | 21 | 12 | 252
PRJ-001 | EMP-009 | Aweys Barre | Shaqaale Caadi | Abriil 2026 | 24 | 12 | 288
PRJ-001 | EMP-009 | Aweys Barre | Shaqaale Caadi | Maajo 2026 | 24 | 12 | 288
PRJ-001 | EMP-009 | Aweys Barre | Shaqaale Caadi | Juun 2026 | 20 | 12 | 240
PRJ-001 | EMP-010 | Bashiir Yuusuf | Shaqaale Caadi | Janaayo 2026 | 24 | 12 | 288
PRJ-001 | EMP-010 | Bashiir Yuusuf | Shaqaale Caadi | Febraayo 2026 | 21 | 12 | 252
PRJ-001 | EMP-010 | Bashiir Yuusuf | Shaqaale Caadi | Maarso 2026 | 25 | 12 | 300
PRJ-001 | EMP-010 | Bashiir Yuusuf | Shaqaale Caadi | Abriil 2026 | 25 | 12 | 300
PRJ-001 | EMP-010 | Bashiir Yuusuf | Shaqaale Caadi | Maajo 2026 | 25 | 12 | 300
PRJ-001 | EMP-010 | Bashiir Yuusuf | Shaqaale Caadi | Juun 2026 | 24 | 12 | 288
PRJ-001 | EMP-011 | Axmed Maxamed | Kaaliye | Janaayo 2026 | 23 | 10 | 230
PRJ-001 | EMP-011 | Axmed Maxamed | Kaaliye | Febraayo 2026 | 21 | 10 | 210
PRJ-001 | EMP-011 | Axmed Maxamed | Kaaliye | Maarso 2026 | 23 | 10 | 230
PRJ-001 | EMP-011 | Axmed Maxamed | Kaaliye | Abriil 2026 | 24 | 10 | 240
PRJ-001 | EMP-011 | Axmed Maxamed | Kaaliye | Maajo 2026 | 22 | 10 | 220
PRJ-001 | EMP-011 | Axmed Maxamed | Kaaliye | Juun 2026 | 20 | 10 | 200
PRJ-001 | EMP-012 | Saciid Aadan | Shaqaale Caadi | Janaayo 2026 | 21 | 12 | 252
PRJ-001 | EMP-012 | Saciid Aadan | Shaqaale Caadi | Febraayo 2026 | 25 | 12 | 300
PRJ-001 | EMP-012 | Saciid Aadan | Shaqaale Caadi | Maarso 2026 | 23 | 12 | 276
PRJ-001 | EMP-012 | Saciid Aadan | Shaqaale Caadi | Abriil 2026 | 22 | 12 | 264
PRJ-001 | EMP-012 | Saciid Aadan | Shaqaale Caadi | Maajo 2026 | 22 | 12 | 264
PRJ-001 | EMP-012 | Saciid Aadan | Shaqaale Caadi | Juun 2026 | 21 | 12 | 252
PRJ-001 | EMP-013 | Yahye Maxamed | Mashiin / Mixer Operator | Janaayo 2026 | 21 | 20 | 420
PRJ-001 | EMP-013 | Yahye Maxamed | Mashiin / Mixer Operator | Febraayo 2026 | 22 | 20 | 440
PRJ-001 | EMP-013 | Yahye Maxamed | Mashiin / Mixer Operator | Maarso 2026 | 20 | 20 | 400
PRJ-001 | EMP-013 | Yahye Maxamed | Mashiin / Mixer Operator | Abriil 2026 | 20 | 20 | 400
PRJ-001 | EMP-013 | Yahye Maxamed | Mashiin / Mixer Operator | Maajo 2026 | 23 | 20 | 460
PRJ-001 | EMP-013 | Yahye Maxamed | Mashiin / Mixer Operator | Juun 2026 | 20 | 20 | 400

## Monthly Payroll
Mushaharka Billaha ah
Employee ID | Magaca | Doorka | Project | Bisha | Gross Salary | Deduction | Net Salary | Status
EMP-001 | Xuseen Ismaaciil | Maamule Mashruuc | PRJ-001 | Janaayo 2026 | 700 | 0 | 700 | La bixiyay
EMP-001 | Xuseen Ismaaciil | Maamule Mashruuc | PRJ-001 | Febraayo 2026 | 700 | 0 | 700 | La bixiyay
EMP-001 | Xuseen Ismaaciil | Maamule Mashruuc | PRJ-001 | Maarso 2026 | 700 | 0 | 700 | La bixiyay
EMP-001 | Xuseen Ismaaciil | Maamule Mashruuc | PRJ-001 | Abriil 2026 | 700 | 0 | 700 | La bixiyay
EMP-001 | Xuseen Ismaaciil | Maamule Mashruuc | PRJ-001 | Maajo 2026 | 700 | 0 | 700 | La bixiyay
EMP-001 | Xuseen Ismaaciil | Maamule Mashruuc | PRJ-001 | Juun 2026 | 700 | 0 | 700 | La bixiyay
EMP-002 | Daahir Sheekh | Injineer Goobta | PRJ-001 | Janaayo 2026 | 550 | 0 | 550 | La bixiyay
EMP-002 | Daahir Sheekh | Injineer Goobta | PRJ-001 | Febraayo 2026 | 550 | 0 | 550 | La bixiyay
EMP-002 | Daahir Sheekh | Injineer Goobta | PRJ-001 | Maarso 2026 | 550 | 0 | 550 | La bixiyay
EMP-002 | Daahir Sheekh | Injineer Goobta | PRJ-001 | Abriil 2026 | 550 | 0 | 550 | La bixiyay
EMP-002 | Daahir Sheekh | Injineer Goobta | PRJ-001 | Maajo 2026 | 550 | 0 | 550 | La bixiyay
EMP-002 | Daahir Sheekh | Injineer Goobta | PRJ-001 | Juun 2026 | 550 | 0 | 550 | La bixiyay
EMP-003 | Maxamed Cumar | Agaasime Guud / Kormeer | PRJ-001 | Janaayo 2026 | 900 | 0 | 900 | La bixiyay
EMP-003 | Maxamed Cumar | Agaasime Guud / Kormeer | PRJ-001 | Febraayo 2026 | 900 | 0 | 900 | La bixiyay
EMP-003 | Maxamed Cumar | Agaasime Guud / Kormeer | PRJ-001 | Maarso 2026 | 900 | 0 | 900 | La bixiyay
EMP-003 | Maxamed Cumar | Agaasime Guud / Kormeer | PRJ-001 | Abriil 2026 | 900 | 0 | 900 | La bixiyay
EMP-003 | Maxamed Cumar | Agaasime Guud / Kormeer | PRJ-001 | Maajo 2026 | 900 | 0 | 900 | La bixiyay
EMP-003 | Maxamed Cumar | Agaasime Guud / Kormeer | PRJ-001 | Juun 2026 | 900 | 0 | 900 | La bixiyay
EMP-004 | Cabdi Nuur Xasan | Xisaabiye Mashruuc | PRJ-001 | Janaayo 2026 | 500 | 0 | 500 | La bixiyay
EMP-004 | Cabdi Nuur Xasan | Xisaabiye Mashruuc | PRJ-001 | Febraayo 2026 | 500 | 0 | 500 | La bixiyay
EMP-004 | Cabdi Nuur Xasan | Xisaabiye Mashruuc | PRJ-001 | Maarso 2026 | 500 | 0 | 500 | La bixiyay
EMP-004 | Cabdi Nuur Xasan | Xisaabiye Mashruuc | PRJ-001 | Abriil 2026 | 500 | 0 | 500 | La bixiyay
EMP-004 | Cabdi Nuur Xasan | Xisaabiye Mashruuc | PRJ-001 | Maajo 2026 | 500 | 0 | 500 | La bixiyay
EMP-004 | Cabdi Nuur Xasan | Xisaabiye Mashruuc | PRJ-001 | Juun 2026 | 500 | 0 | 500 | La bixiyay
EMP-005 | Saalax Axmed | Kormeeraha Shaqada | PRJ-001 | Janaayo 2026 | 450 | 0 | 450 | La bixiyay
EMP-005 | Saalax Axmed | Kormeeraha Shaqada | PRJ-001 | Febraayo 2026 | 450 | 0 | 450 | La bixiyay
EMP-005 | Saalax Axmed | Kormeeraha Shaqada | PRJ-001 | Maarso 2026 | 450 | 0 | 450 | La bixiyay
EMP-005 | Saalax Axmed | Kormeeraha Shaqada | PRJ-001 | Abriil 2026 | 450 | 0 | 450 | La bixiyay
EMP-005 | Saalax Axmed | Kormeeraha Shaqada | PRJ-001 | Maajo 2026 | 450 | 0 | 450 | La bixiyay
EMP-005 | Saalax Axmed | Kormeeraha Shaqada | PRJ-001 | Juun 2026 | 450 | 0 | 450 | La bixiyay

## Subcontractors
Qandaraasyada Shaqada
Contract ID | Shaqada | Qandaraasle | Contract Value | Start | End | Advance 30% | Progress 30% | Progress 20% | Final 20% | Paid To Date | Status
LC-001 | Structural & Concrete Works | Horumar Construction Services | 36000 | 2026-01-15 | 2026-05-31 | 10800 | 10800 | 7200 | 7200 | 36000 | Dhammaystiran
LC-002 | Electrical Installation | Al-Kawthar Electrical Services | 14000 | 2026-03-01 | 2026-06-30 | 4200 | 4200 | 2800 | 2800 | 14000 | Dhammaystiran
LC-003 | Plumbing & Sanitation | Baraka Plumbing & Sanitation | 12000 | 2026-03-01 | 2026-06-30 | 3600 | 3600 | 2400 | 2400 | 12000 | Dhammaystiran
LC-004 | Aluminium, Windows & Doors | Al-Furqaan Windows & Glass | 10000 | 2026-04-01 | 2026-07-31 | 3000 | 3000 | 2000 | 2000 | 8000 | Socda
LC-005 | Painting & Finishing | Iftin Paint & Decor | 9000 | 2026-06-01 | 2026-08-15 | 2700 | 2700 | 0 | 0 | 5400 | Socda

## Materials
Alaabta Dhismaha
Material ID | Date | Alaabta | Unit | Qty | Unit Price | Total | Supplier | Payment Method
MAT-001 | 2026-01-08 | Cement | Bag | 850 | 4.13 | 3506.89 | Hormuud Building Materials | Bank Transfer
MAT-002 | 2026-01-12 | Steel Bars 12m | Piece | 420 | 8.74 | 3669.5 | Al-Furqaan Building Materials | Bank Transfer
MAT-003 | 2026-01-20 | Sand | Truck Load | 35 | 36.4 | 1274.13 | Kaluun Trading & Supplies | Cash
MAT-004 | 2026-01-25 | Gravel / Crushed Stone | Truck Load | 28 | 41.26 | 1155.21 | Kaluun Trading & Supplies | EVC Plus
MAT-005 | 2026-02-06 | Concrete Blocks | Piece | 6500 | 0.27 | 1735.24 | Suuqa Bakaaraha Materials | Bank Transfer
MAT-006 | 2026-02-14 | Timber | Piece | 380 | 5.82 | 2213.35 | Al-Furqaan Building Materials | Cash
MAT-007 | 2026-02-21 | Roofing / Waterproofing Materials | Lot | 1 | 1504.69 | 1504.69 | Kaluun Trading & Supplies | Bank Transfer
MAT-008 | 2026-03-07 | Cement | Bag | 900 | 4.17 | 3756.86 | Hormuud Building Materials | Bank Transfer
MAT-009 | 2026-03-12 | Steel Bars 12m | Piece | 390 | 8.83 | 3445.25 | Hormuud Building Materials | Bank Transfer
MAT-010 | 2026-03-18 | PVC Pipes & Fittings | Lot | 1 | 2038.61 | 2038.61 | Baraka Plumbing Supply | EVC Plus
MAT-011 | 2026-03-26 | Electrical Cables | Lot | 1 | 2523.99 | 2523.99 | Al-Kawthar Electrical Supply | Bank Transfer
MAT-012 | 2026-04-05 | Cement | Bag | 780 | 4.17 | 3255.95 | Hormuud Building Materials | Bank Transfer
MAT-013 | 2026-04-11 | Tiles | Square Meter | 620 | 3.79 | 2347.31 | Suuqa Bakaaraha Materials | Bank Transfer
MAT-014 | 2026-04-19 | Doors & Windows | Set | 24 | 89.8 | 2155.1 | Al-Furqaan Windows & Glass | Bank Transfer
MAT-015 | 2026-04-27 | Paint | Bucket | 85 | 16.5 | 1402.76 | Iftin Paint & Decor | EVC Plus
MAT-016 | 2026-05-06 | Cement | Bag | 700 | 4.22 | 2955.98 | Hormuud Building Materials | Bank Transfer
MAT-017 | 2026-05-13 | Steel Bars 12m | Piece | 330 | 8.88 | 2931.23 | Al-Furqaan Building Materials | Bank Transfer
MAT-018 | 2026-05-21 | Tiles | Square Meter | 540 | 3.83 | 2070.64 | Suuqa Bakaaraha Materials | Cash
MAT-019 | 2026-05-28 | Sanitary Fixtures | Lot | 1 | 1868.72 | 1868.72 | Baraka Plumbing Supply | Bank Transfer
MAT-020 | 2026-06-05 | Electrical Accessories | Lot | 1 | 1504.69 | 1504.69 | Al-Kawthar Electrical Supply | EVC Plus
MAT-021 | 2026-06-13 | Paint | Bucket | 110 | 16.02 | 1761.94 | Iftin Paint & Decor | Bank Transfer
MAT-022 | 2026-06-20 | Flooring / Finishing Materials | Lot | 1 | 2038.61 | 2038.61 | Suuqa Bakaaraha Materials | Bank Transfer
MAT-023 | 2026-06-27 | Water Tanks & Pumps | Lot | 1 | 1383.34 | 1383.34 | Baraka Plumbing Supply | Bank Transfer

## Site Expenses
Kharashaadka Goobta iyo Overhead
Expense ID | Date | Faahfaahin | Category | Amount | Payment Method | Project
EXP-001 | 2026-01-05 | Site office rent | Overhead | 2400 | Bank Transfer | PRJ-001
EXP-002 | 2026-01-10 | Fuel and site transport | Overhead | 3000 | Cash | PRJ-001
EXP-003 | 2026-02-15 | Generator and electricity | Utilities | 1800 | EVC Plus | PRJ-001
EXP-004 | 2026-03-15 | Water, sanitation and site services | Utilities | 1600 | Cash | PRJ-001
EXP-005 | 2026-04-15 | Safety equipment and PPE | Safety | 2200 | Bank Transfer | PRJ-001
EXP-006 | 2026-05-15 | Small tools and equipment maintenance | Equipment | 2400 | Bank Transfer | PRJ-001
EXP-007 | 2026-06-15 | Site security and miscellaneous | Overhead | 1600 | Cash | PRJ-001

## Cash Ledger
Dhaqdhaqaaqa Lacagta iyo Halka Ay Aadeen
Transaction ID | Date | Nooca | Category | Faahfaahin | Project | Income | Expense | Payment Method | Money Destination
TXN-001 | 2026-01-03 | Dakhli | Funding | Owner Capital - Initial Funding | PRJ-001 | 50000 | 0 | Bank Transfer | Owner / Investor Account
TXN-002 | 2026-03-01 | Dakhli | Funding | Owner Capital - Second Funding | PRJ-001 | 40000 | 0 | Bank Transfer | Owner / Investor Account
TXN-003 | 2026-05-15 | Dakhli | Funding | Owner Capital - Third Funding | PRJ-001 | 30000 | 0 | Bank Transfer | Owner / Investor Account
TXN-004 | 2026-06-10 | Dakhli | Funding | Client/Investor Advance for Rental Units | PRJ-001 | 20000 | 0 | Bank Transfer | Owner / Investor Account
TXN-005 | 2026-06-30 | Kharash | Project Cost | Daily labor - Jan-Jun | PRJ-001 | 0 | 15565 | Mixed | Workers / Daily Wage Payroll
TXN-006 | 2026-06-30 | Kharash | Project Cost | Monthly payroll - Jan-Jun | PRJ-001 | 0 | 18600 | Mixed | Monthly Staff Payroll
TXN-007 | 2026-06-30 | Kharash | Project Cost | Subcontractors paid to date | PRJ-001 | 0 | 75400 | Mixed | Subcontractor Accounts
TXN-008 | 2026-06-30 | Kharash | Project Cost | Materials purchased - Jan-Jun | PRJ-001 | 0 | 52499.99 | Mixed | Material Suppliers
TXN-009 | 2026-06-30 | Kharash | Project Cost | Site expenses and overhead | PRJ-001 | 0 | -37204.98 | Mixed | Site Operations / Vendors
TXN-010 | 2026-01-08 | Kharash | Alaab Dhismo | Cement - Hormuud Building Materials | PRJ-001 | 0 | 3506.89 | Bank Transfer | Hormuud Building Materials
TXN-011 | 2026-01-12 | Kharash | Alaab Dhismo | Steel Bars 12m - Al-Furqaan Building Materials | PRJ-001 | 0 | 3669.5 | Bank Transfer | Al-Furqaan Building Materials
TXN-012 | 2026-01-20 | Kharash | Alaab Dhismo | Sand - Kaluun Trading & Supplies | PRJ-001 | 0 | 1274.13 | Cash | Kaluun Trading & Supplies
TXN-013 | 2026-01-25 | Kharash | Alaab Dhismo | Gravel / Crushed Stone - Kaluun Trading & Supplies | PRJ-001 | 0 | 1155.21 | EVC Plus | Kaluun Trading & Supplies
TXN-014 | 2026-02-06 | Kharash | Alaab Dhismo | Concrete Blocks - Suuqa Bakaaraha Materials | PRJ-001 | 0 | 1735.24 | Bank Transfer | Suuqa Bakaaraha Materials
TXN-015 | 2026-02-14 | Kharash | Alaab Dhismo | Timber - Al-Furqaan Building Materials | PRJ-001 | 0 | 2213.35 | Cash | Al-Furqaan Building Materials
TXN-016 | 2026-02-21 | Kharash | Alaab Dhismo | Roofing / Waterproofing Materials - Kaluun Trading & Supplies | PRJ-001 | 0 | 1504.69 | Bank Transfer | Kaluun Trading & Supplies
TXN-017 | 2026-03-07 | Kharash | Alaab Dhismo | Cement - Hormuud Building Materials | PRJ-001 | 0 | 3756.86 | Bank Transfer | Hormuud Building Materials
TXN-018 | 2026-03-12 | Kharash | Alaab Dhismo | Steel Bars 12m - Hormuud Building Materials | PRJ-001 | 0 | 3445.25 | Bank Transfer | Hormuud Building Materials
TXN-019 | 2026-03-18 | Kharash | Alaab Dhismo | PVC Pipes & Fittings - Baraka Plumbing Supply | PRJ-001 | 0 | 2038.61 | EVC Plus | Baraka Plumbing Supply
TXN-020 | 2026-03-26 | Kharash | Alaab Dhismo | Electrical Cables - Al-Kawthar Electrical Supply | PRJ-001 | 0 | 2523.99 | Bank Transfer | Al-Kawthar Electrical Supply
TXN-021 | 2026-04-05 | Kharash | Alaab Dhismo | Cement - Hormuud Building Materials | PRJ-001 | 0 | 3255.95 | Bank Transfer | Hormuud Building Materials
TXN-022 | 2026-01-15 | Kharash | Qandaraas | Structural & Concrete Works - Horumar Construction Services - Advance | PRJ-001 | 0 | 10800 | Bank Transfer | Horumar Construction Services
TXN-023 | 2026-03-01 | Kharash | Qandaraas | Electrical Installation - Al-Kawthar Electrical Services - Advance | PRJ-001 | 0 | 4200 | Bank Transfer | Al-Kawthar Electrical Services
TXN-024 | 2026-03-01 | Kharash | Qandaraas | Plumbing & Sanitation - Baraka Plumbing & Sanitation - Advance | PRJ-001 | 0 | 3600 | Bank Transfer | Baraka Plumbing & Sanitation

## Budget vs Actual
Miisaaniyadda iyo Kharashka Dhabta ah
Qaybta | Amount | % Budget
Shaqaalaha Maalinlaha | 15565 | 8.65%
Mushaharka Billaha | 18600 | 10.33%
Qandaraasleyaasha | 75400 | 41.89%
Alaabta Dhismaha | 52499.99 | 29.17%
Site Expenses / Overhead | 15000 | 6%
WADARTA LA BIXIYAY | 177065 | 70.83%
MIISAANIYADDA | 250000 | 100%
HARAAGA | 72935 | 29.17%

## Progress
Horumarka Dhismaha
Work Package | Progress % | Status
Site Preparation & Foundation | 100% | Dhammaystiran
Ground Floor Structure | 100% | Dhammaystiran
Floors 1-3 Structure | 100% | Dhammaystiran
Floors 4-5 Structure | 75% | Socda
Blockwork & Internal Walls | 70% | Socda
Electrical First Fix | 65% | Socda
Plumbing First Fix | 65% | Socda
Doors & Windows | 55% | Socda
Plastering & Finishing | 45% | Socda
Painting | 20% | Bilowday
External Works | 10% | Bilowday
OVERALL PHYSICAL PROGRESS | 70% | Socda

## Monthly Summary
Soo Koobidda Kharashka Bil kasta
Bisha | Daily Labor | Monthly Payroll | Subcontractors | Materials | Overhead | Total Spent
Janaayo 2026 | 2621 | 3100 | 10800 | 9605.73 | 2400
Febraayo 2026 | 2491 | 3100 | 0 | 5453.28 | 3000
Maarso 2026 | 2627 | 3100 | 10800 | 11764.71 | 1800
Abriil 2026 | 2650 | 3100 | 10800 | 9161.12 | 1600
Maajo 2026 | 2673 | 3100 | 7200 | 9826.57 | 2200
Juun 2026 | 2503 | 3100 | 7200 | 6688.58 | 2400